## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
D1 | Niveditha | 2026-01-02 | PDF parsing failure | Ingestion | Development | Logical | Used pypdf to ingest PDF files. | 2026-01-03 | Closed | Parsing working correctly
D2 | Niveditha | 2026-01-12 | API timeout | Embedding | Development | Performance | Used tenacity to avoid API timeout | 2026-01-13 | Closed | Timeout resolved after retry logic
D3 | Niveditha | 2026-01-25 | Irrelevant chunks | Retrieval | Development | Data | Used vector embeddings and LLM model to retrieve relevant chuncks | 2026-01-27 | Closed | Relevant chunks retrieved accurately
D4 | Niveditha | 2026-02-10 | Memory loss in session | Chatbot | Development | System | Used cloud to store data and avoid data/memory loss | 2026-02-12 | Closed | Session persistence stable
D5 | Niveditha | 2026-02-28 | Slow response | UI | Development | Performance | Used lovable to create a user interactive interface and for a faster response. | 2026-03-02 | Closed | UI response speed improved

## Sheet2
Logical
User Interface
Maintainability
Standards
Others